## Sheet1
Sr. No. | Brand | Action Item | Mode | Time (minutes) |  | Sprintx-3 | PCSINT | Sprintx-3 | PCSINT | Sprintx-3 | PCSINT | PCSINT | PRE-PROD | Remarks | Can be automated ? | Remarks | SPRINTx-1 |  |  |  | Username/Password
|  |  |  | Old Env. | New Env. |  |  | 191220 | 191220 | 191229 | 191229 | 200110 | 200110 |  |  |  | DS Technology/Brand | Status | URL | Open issues / Known issues (if any)
1 | Preparation | Send downtime notice to updated mailing list : \\lp5-ndk-ind\bitbucket\ciws\Mail_Delivery_List.txt | Manual | 1 | 1 | Done | Done | Done | Done | Done | Done | Done | Not-Done |  | jenkins job - that automatically triggers at 3 PM AWST and can trigger build job at 5 PM AWST | Downtime notice not required for pre-prod as it is not yet commisioned | ENOVIA | Done | https://per0dvoy51.apac.ent.bhpbilliton.net/3dspace
2 |  | Generate builds for Enovia, Catia, Quintiq, Biovia, Exalead | Automated | 15 | 15 | Done | Done | Done | Done | Done | Done | Done | Done |  | can be | Using same build for PCSINT and Preprod - P3S0R1.SPR3.200110 | QUINTIQ | Done | http://10.241.170.50:6300/webapp/BHPVoyagerIPS/
3 |  | Tag all branches | Manual | 5 | 5 | Done | Done | Done | Done | Done | Done | Done | Done |  | can be -> check with shrikant | Using same build for PCSINT and Preprod - P3S0R1.SPR3.200110 | NATIVE CLIENT | Done | https://per0dvoy51.apac.ent.bhpbilliton.net/3dspace
4 | ENOVIA | Enovia build deployment | Automated |  |  | Done | Done | Done | Done | Not-Done | Not-Done | Done | Not-Done |  |  | We see spinner errors in console but not in the spinner error log | EXALEAD | Done | http://per0dvoy58.apac.ent.bhpbilliton.net:20000/bhp-voyager
5 |  | PnO Import | Manual |  |  | NA | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | * to be automated - ask Rohit/Vishal to commit the files | can be -once pno is finalized | To be done by infra - will be handover to CICD once PnO is finalized | BIOVIA | Done | https://per0dvoy59.apac.ent.bhpbilliton.net:9943
6 |  | Spinner Instllation | Manual | 0 | 10 | NA | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | * to be automated | can be
7 |  | admin_platform user type system | Manual |  |  | NA | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | * to be automated | can be part of onetime scripts for new env |  | SPRINTx-2
8 |  | Take staging folder backup | Automated |  |  | Not done | Not done | Done | Done | Not-Done | Not-Done | Done | Not-Done | * Step to be added from next deployments |  | No change in code hence no deployment done | DS Technology/Brand | Status | URL | Open issues / Known issues (if any)
9 |  | Take database backup | Manual |  |  | Not done | Not done | Done | Done | Not-Done | Not-Done | Done | Not-Done | * need access to database on pcs-int environment | can be - need infra help |  | ENOVIA | Done | https://per0dvoy52.apac.ent.bhpbilliton.net/3dspace
10 |  | Activate mine geologist group 2.0.3 | Manual |  |  | Done | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done |  |  |  | QUINTIQ | Done | http://10.241.170.50:6300/webapp/BHPVoyagerIPS/
11 |  | Add members to the group | Manual |  |  | Done | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done |  |  |  | NATIVE CLIENT | Done | https://per0dvoy52.apac.ent.bhpbilliton.net/3dspace
12 |  | Run \onetimescripts\Member_List_Creation.tcl | Automated |  |  |  |  | Done | Done | Not-Done | Not-Done | OTA-Done | Not-Done |  |  |  | EXALEAD | Done | http://per0dvoy58.apac.ent.bhpbilliton.net:20000/bhp-voyager
13 |  | Execute CAPA_Template_Creation.tcl | Automated |  |  | NA | Done | Done | Done | Not-Done | Not-Done | OTA-Done | Not-Done | * Issue in CAPA template - not visible |  |  | BIOVIA | Done | https://per0dvoy59.apac.ent.bhpbilliton.net:9943
14 |  | Import rdf file | Manual |  |  | NA | Done | Done | Done | Not-Done | Not-Done | OTA-Done | Not-Done
15 |  | onetimescript/PendingTaskNotificationSchedular | Manual |  |  | NA | Done | Done | Done | Not-Done | Not-Done | OTA-Done | Not-Done
16 |  | ExecuteJPO.bat | Automated |  |  | Not done | Not done | Done | Done | Not-Done | Not-Done | OTA-Done | Not-Done | * details available in confluence
17 |  | copy filtering.jar to correct location or change mxclasspath in enovia.ini | Automated |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done |  |  |  | SPRINTx-3
18 |  | approval route template, project template and issue template loaded as part of the deployment | Automated |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done |  |  |  | DS Technology/Brand | Status | URL | Remarks /Open issues / Known issues (if any)
19 |  | compile all jpo | Automated | [8 empty] | Done | Done
20 |  | resource gantt deployment | Manual | [8 empty] | OTA-Done |  |  |  | Failing on pre-prod
21 |  | Dashboard creation and share with all users | Manual |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done |  |  |  | ENOVIA | Done | https://per0dvoy53.apac.ent.bhpbilliton.net/3dspace | No deployement done as there are no new code commit
22 | QUINTIQ | Quintiq database backup | *Automated |  |  | Done | Not done | Done | Not-Done | Not-Done | Not-Done | Done | Not-Done | * need access to database on pcs-int environment |  | No change in code hence no deployment done on pcsint | QUINTIQ | Done | http://10.241.170.50:6300/webapp/BHPVoyagerIPS/ | No deployement done as there are no new code commit
23 |  | Quintiq deployment | Automated |  |  | Done | Done | Done | Done | Not-Done | Not-Done | Done | Done |  |  |  | NATIVE CLIENT | Done | https://per0dvoy53.apac.ent.bhpbilliton.net/3dspace | \\entper-fil01\voy_dev_app_data\Native_Client_Deployments
24 |  | Post deployment validation | Manual |  |  | Done | Done | Done | Done | Not-Done | Not-Done | Done | Not-Done | * Validation step failed for pcsint |  |  | EXALEAD | Done | http://per0dvoy58.apac.ent.bhpbilliton.net:20000/bhp-voyager
25 | NATIVE CLIENT (CATIA DELMIA CAA | Deploy new debug kit if any | Manual | [8 empty] | OTA-Done | OTA-Done |  |  | Debug kit 10 deployed on 13012020
26 |  | provide required list of licesnses to admin_platform user | Manual | [8 empty] | OTA-Done | OTA-Done
27 |  | admin_platform user needs to have leader and owner role for the 3dxml steps - add role | Manual | [8 empty] | OTA-Done | OTA-Done
28 |  | You need to have TXO license in order to view BHP custom applicatoins | Manual | [8 empty] | OTA-Done | OTA-Done
29 |  | Import 3dxml from Gautam M. | Manual |  |  | Done | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | BIOVIA | Done | https://per0dvoy59.apac.ent.bhpbilliton.net:9943 | Regression test failure. Awaiting response from Dev. lead
30 |  | Import 3dxml senthil | Manual |  |  | Done | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone
31 |  | Import 3dxml - 1.5 GB from senthil | Manual |  |  | Done | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | PCS-INT
32 |  | bind -> data setup | Manual |  |  | Done | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | DS Technology/Brand | Status | URL | Remarks/Open issues / Known issues (if any)
33 |  | bind2 -> data setup | Manual |  |  | Done | Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | ENOVIA |  | https://per0dvoy69.apac.ent.bhpbilliton.net/3dspace | No deployement done as there are no new code commit
34 |  | Deploy/Install applications | Manual |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | QUINTIQ |  | http://10.241.170.69:6300/webapp/BHPVoyagerIPS/ | No deployement done as there are no new code commit
35 |  | Data ingestion step - 9GB filed from Gautam | Manual |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | QUINTIQ Alternate URL |  | http://per0dvoy81.apac.ent.bhpbilliton.net:6300/webapp/BHPVoyagerIPS/
36 |  | validation step after import - search mphase attribute | [9 empty] | OTA-Done | OTA-NotDone |  |  |  | NATIVE CLIENT |  | https://per0dvoy69.apac.ent.bhpbilliton.net/3dspace | \\entper-fil01\voy_dev_app_data\Native_Client_Deployments
37 |  | Resource tables (color pallate and symentic dictionary import) | Manual |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | EXALEAD |  | http://per0dvoy80.apac.ent.bhpbilliton.net:30000/bhp-voyager
38 |  | Import ER94 3dxml | Manual | [8 empty] | OTA-Done | OTA-NotDone |  |  |  | BIOVIA |  | https://per0dvoy79.apac.ent.bhpbilliton.net:9943/ | Regression test failure. Awaiting response from Dev. lead
39 |  | Server side deployment on BHP 3dingestion server per0dvoy72.apac.ent.bhpbilliton.net | Manual | [8 empty] | OTA-Done | OTA-NotDone |  |  | Check with Anurag Mangal | Ingestion/ Batch Server |  | http://per0dvoy72.apac.ent.bhpbilliton.net:9944/voyager/invoke3dspaceload
40 |  | BI Essentials deployment (same as debig kit - create env file from env. editor.) | [7 empty] | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone
41 | EXALEAD | Get app.properties from Exalead dev Amit N./Anil C. or create it | Manual |  |  | Done | Done | Done | Done | Done | Done | Done | Done | Check with Amit N. about automation/bitbucket
42 |  | Configure Jenkins slave on target server | Manual | [8 empty] | OTA-Done | OTA-Done
43 |  | Exalead Deployment | Automated |  |  | Done | Done | Done | Done | Done | Done | Done | Done
44 |  | Install studio if now already installed | Manual | [8 empty] | OTA-Done | OTA-Done
45 |  | Check License server file exist or not - create license file if not | Manual | [8 empty] | OTA-Done | OTA-Done
46 |  | One time activity for each new environement - Matrix.R file and mql connection | Manual |  |  | Done | Pending | Done | Done | Done | Done | Done | OTA-Done |  |  |  | PRE-PROD
47 |  | Setup NOVIA_DEVIATIONS_THREASHHOLDS connector of Type ENOVIA V6 | Manual | [8 empty] | OTA-Done | OTA-Done |  |  |  | DS Technology/Brand | Status | URL | Remarks/Open issues / Known issues (if any)
48 |  | One time activity for each new environement - Setup job orchastrator | Manual |  |  | Done | Pending | OTA-NotDone | Done | OTA-NotDone | Done | Done | OTA-NotDone |  |  |  | ENOVIA |  | https://per0qvoy11.apac.ent.bhpbilliton.net/3dspace
49 |  | One time activity for each new environement - Setup Enovia V6 connector | Manual |  |  | Done | Pending | Done | Done | Done | Done | Done | OTA-Done |  |  |  | QUINTIQ |  | http://per0qvoy21:6300/webapp/BHPVoyagerIPS/ |  | administrator / no password
50 |  | Setup for deviation notification | Manual |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone | To be automated - check with kartik |  |  | QUINTIQ Alternate URL |  | http://10.241.170.95:6300/webapp/BHPVoyagerIPS/ | \\entper-fil01\voy_dev_app_data\Native_Client_Deployments
51 |  | Post deployment validation | Manual |  |  | Done | Done | Done | Done | Done | Done | Done | Done | * Validation step failed for pcsint and sprintx3 |  |  | NATIVE CLIENT |  | https://per0qvoy11.apac.ent.bhpbilliton.net/3dspace
52 | BIOVIA | Biovia deployment | Automated |  |  |  |  | Done | Done | Done | Done | Done | Done |  |  |  | EXALEAD CV |  | http://per0qvoy20.apac.ent.bhpbilliton.net:30000/bhp-voyager |  | admin / Passw0rd
53 |  | Post deployment configuration | Automated |  |  |  |  | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-Done | OTA-NotDone |  |  |  | PLM Analytics |  | http://per0qvoy19.apac.ent.bhpbilliton.net:30000
54 |  | Post deployment validation | Manual |  |  |  |  | Done | Done | Done | Done | Done | OTA-NotDone |  |  |  | BIOVIA |  | https://per0qvoy22.apac.ent.bhpbilliton.net:9943/ | Regression test failure. Awaiting response from Dev. lead | scitegicadmin / scitegic
55 | Finalization | Attach release notes | Manual |  |  | Done | Done | Done | Done | Not-Done | Done | Done | Done |  |  |  | Ingestion/ Batch Server |  | http://per0qvoy18.apac.ent.bhpbilliton.net:9944/voyager/invoke3dspaceload
56 |  | Update CICD Deployment tracker | Manual | [6 empty] | Done | Done | Done | Done
57 |  | Send deployment finished email with URLs to mailing list: \\lp5-ndk-ind\bitbucket\ciws\Mail_Delivery_List.txt | Manual |  |  | Done | Done | Done | Done | Done | Done | Done | Done
58 |  | move the items from “Ready For Testing” to “In Testing” | Manual
[17 empty] | APAC\SA-IOR-VOY-TST |  | dr5S=l?4t??5rU7r
[9 empty] | Done |  | Done |  | Done
[9 empty] | Not-Done |  | Not-Done |  | Not-Done |  |  |  | APAC\SA-IOR-VOY-QA |  | dU47ImBH2Y^K
[9 empty] | OTA-Done |  | OTA-Done |  | OTA-Done |  |  | OTA : One Time Acitivity for each new environment
[9 empty] | OTA-NotDone |  | OTA-NotDone |  | OTA-NotDone | [5 empty] | OYWVy%bmIG*z8Y%~
Note on F4: Author: Downtime notice, build generation and tagging branches are independent of environments - be it old or new

## Sheet2
PRE-PROD
DS Technology/Brand | URL | Remarks/Open issues / Known issues (if any)
ENOVIA | https://per0qvoy11.apac.ent.bhpbilliton.net/3dspace
QUINTIQ | http://per0qvoy21:6300/webapp/BHPVoyagerIPS/
QUINTIQ Alternate URL | http://10.241.170.95:6300/webapp/BHPVoyagerIPS/ | \\entper-fil01\voy_dev_app_data\Native_Client_Deployments
NATIVE CLIENT | https://per0qvoy11.apac.ent.bhpbilliton.net/3dspace
EXALEAD CV | http://per0qvoy20.apac.ent.bhpbilliton.net:30000/bhp-voyager
PLM Analytics | http://per0qvoy19.apac.ent.bhpbilliton.net:30000
BIOVIA | https://per0qvoy22.apac.ent.bhpbilliton.net:9943/ | Regression test failure. Awaiting response from Dev. lead
Ingestion/ Batch Server | http://per0qvoy18.apac.ent.bhpbilliton.net:9944/voyager/invoke3dspaceload
PRE-PROD
DS Technology/Brand | URL | Remarks/Open issues / Known issues (if any)
ENOVIA | https://per0qvoy11.apac.ent.bhpbilliton.net/3dspace
QUINTIQ | http://per0qvoy21:6300/webapp/BHPVoyagerIPS/ | OOTB installation complete, configuration in progress, ETA : Today / 15th Jan.
QUINTIQ Alternate URL | http://10.241.170.95:6300/webapp/BHPVoyagerIPS/ | \\entper-fil01\voy_dev_app_data\Native_Client_Deployments
NATIVE CLIENT | https://per0qvoy11.apac.ent.bhpbilliton.net/3dspace
EXALEAD CV | http://per0qvoy20.apac.ent.bhpbilliton.net:30000/bhp-voyager
PLM Analytics | http://per0qvoy19.apac.ent.bhpbilliton.net:30000
BIOVIA | https://per0qvoy22.apac.ent.bhpbilliton.net:9943/
Data ingestion | N.A. | (ODR) : Available data is being indexed (e.g. ODR ), we have a major issue on BMF converter due to which Voy-092 is failing (impacting 3 data sets), activity to continue into tomorrow. File base : Two day behind schedule, as requires all core product deployments complete, also impacted by BMF converter issue. ETA Tomorrow to start. IIB data ingestion : Complete, data flowing.